## Time and action calendar
Time & Action Calendar
| Buyer | Greece | Order Qty. | 2000 |  | Ex-factory date (on PO)
| Style # | 4041 | Merchant | Aman |  | Ex-factory date(as per plan) |  |  | 2009-01-08
| Style Description | Dress | Recvd Date | 2008-11-20 |  | Lead Time (days) |  |  | 49
| Key Processes | Planned Start | Planned End | Duration (days) | Actual start | Actual End | Duration (days) | Responsibility |  | Remarks
1 | Order receipt (Buyer PO) | 2008-11-20 | [5 empty] | Merchant
2 | Consumption calculation | 2008-11-21 | [5 empty] | Pattern master
3 | BOM generation | 2008-11-23 | [5 empty] | Merchant
4 | PO issue for Fabric, trims | 2008-11-24 | [5 empty] | Store Mngr. (Fabric/Trim)
5 | Size set submission | 2008-11-25 | [5 empty] | Merchant
6 | Size set Comments | 2008-11-28 | [5 empty] | Merchant
7 | PP meeting | 2008-12-01 | [5 empty] | Merchant
8 | Production planning updates and circulation | 2008-12-11 |  | 10 |  |  |  | Production Manager
9 | Fabric in-house | 2008-11-24 | 2008-12-08 | 15 |  |  |  | Store Mngr. (Fabric/Trim)
10 | Trims In-house | 2008-11-24 | 2008-12-03 | 10 |  |  |  | Store Mngr. (Fabric/Trim)
11 | Cutting | 2008-12-11 | 2008-12-12 12:00 | 2.5 |  |  |  | Cutting in charge
12 | Fabrication/stitching | 2008-12-26 12:00 | 2008-12-30 20:00 | 5.3333 |  |  |  | Production Manager
13 | Finishing | 2008-12-31 12:00 | 2009-01-03 12:00 | 4 |  |  |  | Finishing In charge
14 | Packing | 2009-01-02 12:00 | 2009-01-06 12:00 | 5 |  |  |  | Finishing In charge
15 | Inspection | 2009-01-07 12:00 | [5 empty] | QC
16 | Dispatch | 2009-01-08 12:00 | [5 empty] | Finishing In charge